## Timeline
The Crick Bick Company
|  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
TASK | RESPONSIBLE | DESCRIPTION | DUE DATE | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Use project tasks and main events to group your activities | Identify who will be responsible for leading this activity | Describe the activity undertaken in this task | Create a simple Gantt chart by blocking out the duration of the task. Key events during the task can be marked with an X
Project Phase I
Wimblo Bimblo Project Design | Pim Davis | Complete creative design | 2002-04-08 | [13 empty] | X
|  | - Round one creative review | 2002-02-11 | [5 empty] | X
|  | - Round two creative review | 2002-04-01 | [12 empty] | X
|  | - Design completion meeting | 2002-04-08 | [13 empty] | X
Griggle Production | Jeremy DeMognn | Production of assets | 2002-07-07 | [24 empty] | X
Smiling Friends Statistics Monitoring | Shrimpina | Report on key project metrics after completion | Monthly thru EOY | [28 empty] | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  | X
Project Phase II
Spinto Bean Design | Kellan Marshall | Design our Beans | 2003-02-26 | [7 empty] | X
|  | - Round one creative review | 2003-01-22 |  |  | X
|  | - Round two creative review | 2003-02-19 | [6 empty] | X
|  | - Design completion meeting | 2003-02-26 | [7 empty] | X
Production of Spinto Beans | Kyle Plume | Production of Beans and Cans for Beans | 2003-05-14 | [18 empty] | X
Monitoring of Sales | Jeff Bezos | Monitor and report sales | End of month through EOY | [23 empty] | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X

## Budget & Expenses
PROJECT BUDGET PER TASK
Insert a chart into a presentation by selecting the data to include in the chart, then go to Insert > Chart and customize your chart using the "Chart Editor".
Phase 1
| Task 1-1 | 10500
| Task 1-2 | 15000
| Task 1-3 | 5000
Phase 2
| Task 2-1 | 5000
| Task 2-2 | 13000 |  | You can adjust the colors to match a slide presentation by clicking on a piece of the chart and selecting another color.
| Task 2-3 | 8000
| Total Budget | 56500
Add this chart to a slide presentation by selecting the chart, then click on the arrow in the upper right corner and choose "Copy chart"
PROJECT EXPENSES
| Category | Cost
| Employee Wages | 27500
| Materials | 20500
| Beans | 8500
| Total Expenses | 56500

## Status
PHASE | TASK | STATUS |  | NEXT STEPS | RESPONSIBLE | DUE | COMPLETE | COMMENTS
Group your status line items by project phase | Specify the tasks as outlined in the timeline | State whether the task is tracking to the plan, and use colors to flag problems. * Green (In progress) indicates the task is proceeding as planned. * Yellow (Needs attention) indicates attention is needed. * Red (At risk) flags a task which may jeopardize the project plan. This status document uses drop down menus and conditional formatting to keep the team on track. Learn more at the links below. |  | List the activities required to complete this task | Assign an owner to each activity | List the due date for each activity | Identify whether the activity has been completed
Get help with creating in-cell drop down lists
Get help with using conditional formatting
Phase 1 | Wimblo Bimblo Project Design | Completed | Completed | - Define timeline - Enter budget data - Set up status - Add key docs - Populate contacts tab - Include completed tab | Pim Davis | 2002-04-08 | Yes
| Griggle Production | Needs attention | Needs attention | - Create timelines - Update status - Change color column to illustrate project on track, slipping or in danger. | Jeremy DeMognn | 2002-07-07 | No
| Smiling Friends Statistics Monitoring | At risk | At risk | - Complete contacts list - Add key docs | Shrimpina | 2002-12-31 | No
Phase 2 | Spinto Bean Design | Completed | Completed | - Define timeline - Define Product - Design Can | Kellan Marshall | 2003-02-26 | No
| Production of Spinto Beans | At risk | At risk | - Create Beans - Create Bean Cans - Put Beans in Cans | Kyle Plume | 2003-05-14 | No
| Monitoring of Sales | Needs attention | Needs attention | - Monitor Sales numbers - Aggregate Data | Jeff Bezos | 2003-12-31 | No

## Sample data
To create pivot tables with your data, click Data > Pivot table.
Need help? Try this interactive lesson on pivot tables.
division | subdivision | product number | number of units | price per unit
east | 6 | 1 | 15 | 9
east | 5 | 1 | 16 | 10
west | 4 | 1 | 12 | 9
west | 5 | 1 | 22 | 8
east | 6 | 1 | 17 | 7
west | 6 | 1 | 19 | 11
east | 5 | 1 | 12 | 8
east | 4 | 2 | 11 | 8
east | 3 | 2 | 10 | 12
west | 5 | 2 | 13 | 9
west | 3 | 2 | 16 | 9
east | 4 | 2 | 13 | 8
west | 6 | 2 | 17 | 11
east | 3 | 2 | 13 | 8

## Status options (hidden)
Status bar options
(hide this worksheet within the working document; changes made here will update the dropdown options on the Status tab)
Drop down menu items below
In progress
Needs attention
At risk
Completed